# Dance-a-Thon Planning Checklist

Every task with an owner and a done box. Weeks follow the school-day plan (fundraising opens three weeks before the event). Add your own names in the Owner column.

## Week by week

| Task | Owner | Due | Done |
| --- | --- | --- | --- |
| 8 weeks out · Decide |  |  |  |
| Choose the date, format, length and fundraising goal; get approval from the principal, board or venue | Chair with principal or board |  | ☐ |
| Name leads for music, safety, volunteers, money and communications | Chair |  | ☐ |
| Draft the budget and pick the donation model (flat, per song, per hour or a mix; decide on caps) | Treasurer |  | ☐ |
| Book the gym or venue; sign the facility-use agreement and ask which certificate of insurance it requires | Facilities lead |  | ☐ |
| 7 weeks out · Book & approve |  |  |  |
| Confirm the music plan and ask the district or venue who covers public-performance licensing | Music lead |  | ☐ |
| Book the DJ or sound; agree a sound-level plan and a quieter zone away from the speakers | Music lead |  | ☐ |
| Decide on lighting: strobe or flashing effects on or off (if used, plan advance warnings to families) | Safety lead |  | ☐ |
| Arrange event insurance and send the certificate of insurance to the venue | Treasurer |  | ☐ |
| Reserve custodial, security and setup time on the facility calendar | Facilities lead |  | ☐ |
| 6 weeks out · Build |  |  |  |
| Write the supervision plan: adults per area using your school, district, venue or insurer ratio; sign-in, sign-out, release only to listed adults | Safety lead |  | ☐ |
| Accessibility and sensory plan: quiet room, ear protection, seating, interpreter or captioning requests | Safety lead |  | ☐ |
| Hydration plan: water stations and rest breaks built into the run of show | Safety lead |  | ☐ |
| Ask the school nurse what first aid coverage and supplies the event needs | Safety lead |  | ☐ |
| 5 weeks out · Build |  |  |  |
| Open volunteer recruitment with backups; follow your volunteer screening rules | Volunteer coordinator |  | ☐ |
| Send sponsor asks with the sponsorship proposal and reply form | Sponsorship lead |  | ☐ |
| Finish the pledge sheet and parent letter in English and Spanish (and other home languages) | Communications lead |  | ☐ |
| Set up online giving and decide how cash and checks are turned in and stored | Treasurer |  | ☐ |
| 4 weeks out · Build |  |  |  |
| Plan the kickoff assembly or record a short dance preview video | Communications lead |  | ☐ |
| First playlist review: clean edits only, age-appropriate lyrics | Music lead |  | ☐ |
| Draft the run of show: dance blocks, water and rest, games, announcements | Chair |  | ☐ |
| Share the teacher communication kit and the class schedule with staff | Communications lead |  | ☐ |
| 3 weeks out · Launch fundraising |  |  |  |
| Kickoff: assembly or preview video; pledge sheets and the parent letter go home; online giving opens | Communications lead |  | ☐ |
| Post the flyer and first social post; send donation email 1 | Communications lead |  | ☐ |
| Collect sponsor names and logos for signs and DJ announcements | Sponsorship lead |  | ☐ |
| 2 weeks out · Launch fundraising |  |  |  |
| Mid-campaign reminder and progress update (no individual money leaderboards) | Communications lead |  | ☐ |
| Gather supplies: water and cups, ear protection, wristbands or name tags, signage, first aid kit | Safety lead |  | ☐ |
| Assign volunteers to roles, stations and shifts; send the assignment sheet | Volunteer coordinator |  | ☐ |
| Final week · Final prep |  |  |  |
| Confirm volunteers and shifts; fill gaps from backups (7 days out) | Volunteer coordinator |  | ☐ |
| Final playlist review for clean edits; send the run of show to the DJ (5 days out) | Music lead |  | ☐ |
| Check water, first aid, ear protection and quiet-room supplies; confirm the sound-check time (3 days out) | Safety lead |  | ☐ |
| Send the last-chance donation email and the event-day reminder to families (what to wear, sign-out plan) | Communications lead |  | ☐ |
| Print sign-in and sign-out sheets, the safety plan, rules cards and the tally sheet | Chair |  | ☐ |
| Day-before setup and walk-through: exits, sign-in and sign-out, quiet zone, water, sound check (1 day out) | Facilities lead |  | ☐ |

## Event day

| Task | Owner | Due | Done |
| --- | --- | --- | --- |
| Volunteer briefing: roles, stations, safety plan, lost-child procedure, where the incident log is kept | Volunteer coordinator |  | ☐ |
| Sound check at the planned level; quiet zone set up and signed | Music lead |  | ☐ |
| Walk the exits: every exit unlocked from inside, clear and marked | Facilities lead |  | ☐ |
| First aid station stocked; AED location confirmed; nurse or first aid lead in place | Safety lead |  | ☐ |
| Sign-in opens; dancers counted in; wristbands or name tags on | Sign-in lead |  | ☐ |
| Run the show: dance blocks, water and rest, games, announcements | Chair with DJ |  | ☐ |
| Count songs or hours for per-unit pledges; two people sign off the count | Treasurer |  | ☐ |
| Announce thank-yous to sponsors, staff and volunteers | Chair |  | ☐ |
| Sign-out: release only to adults on the approved list; unclaimed dancers stay with two adults | Sign-out lead |  | ☐ |
| Lock cash and pledge envelopes away; two people count before anyone leaves | Treasurer |  | ☐ |

## Setup (before doors open)

| Task | Owner | Due | Done |
| --- | --- | --- | --- |
| Mark the dance floor edges and keep a clear lane to every exit | Facilities lead |  | ☐ |
| Place speakers facing the floor and away from the quiet zone; tape every cable run | Music lead |  | ☐ |
| Set up the DJ table with power, a backup device and the run of show | Music lead |  | ☐ |
| Water station with cups, refill jugs, trash and a towel for spills | Safety lead |  | ☐ |
| Quiet room or zone: seating, low light, ear protection, a sign, one adult assigned | Safety lead |  | ☐ |
| Sign-in table at the main entrance; sign-out table where adults can wait without crossing the floor | Sign-in lead |  | ☐ |
| Pledge and tally desk away from the floor, with a lockable box | Treasurer |  | ☐ |
| First aid station near an exit, with the incident log and contact list | Safety lead |  | ☐ |
| Post signs: restrooms, water, quiet room, first aid, no food on the dance floor | Facilities lead |  | ☐ |
| Walk-through with the facility contact before doors open | Chair |  | ☐ |

## Teardown

| Task | Owner | Due | Done |
| --- | --- | --- | --- |
| Music down; sign-out complete; headcount matches sign-in | Sign-out lead |  | ☐ |
| Cash and pledge envelopes counted by two people and locked away | Treasurer |  | ☐ |
| Unplug and pack sound and lighting; coil and label cables | Music lead |  | ☐ |
| Collect lost-and-found; note where it will be held | Volunteer coordinator |  | ☐ |
| Clear trash and recycling; wipe spills; remove all tape from the floor | Cleanup crew |  | ☐ |
| Return borrowed and rented items; note anything damaged | Facilities lead |  | ☐ |
| Final walk-through with the facility contact; lights off, doors locked | Chair |  | ☐ |

## After the event

| Task | Owner | Due | Done |
| --- | --- | --- | --- |
| Day 1: Send per-song or per-hour totals to donors and start collecting pledges | Treasurer |  | ☐ |
| Day 3: Pledge reminder 1 | Treasurer |  | ☐ |
| Day 7: Thank-yous to volunteers, sponsors, staff and families | Chair |  | ☐ |
| Day 10: Pledge reminder 2 (final) | Treasurer |  | ☐ |
| Day 21: Close collection; two people count cash; complete the financial report | Treasurer |  | ☐ |
| Day 28: Evaluation meeting: what to keep and change; write handoff notes for next year | Chair |  | ☐ |

## Event-day supplies

☐  Speakers, mixer, playback device and a backup device with the playlist saved offline

☐  Wireless and wired microphones, spare batteries

☐  Extension cords, power strips, gaffer tape, cable covers

☐  Water, cups, refill jugs, trash bags

☐  First aid kit, incident log, contact list

☐  Ear protection for young dancers and anyone who asks

☐  Quiet-room kit: seating, low light, fidgets or calm activities, a visual schedule

☐  Sign-in and sign-out sheets, approved-adult list, pens

☐  Wristbands or name tags

☐  Signage and tape

☐  Pledge envelopes, lockable cash box, tally sheet

☐  Timer or large clock visible to the DJ

☐  Rules cards and the run of show for every lead