# Fun Run Planning Checklist

## Approvals

☐ Principal, board or venue approves the date, backup date and format in writing

☐ District rules checked: facility use, fundraising, money handling, flyers

☐ Insurance confirmed for the group running the event, not just the school

☐ Certificates of insurance requested for every venue that asks

☐ Route runs: permit filed by the city's deadline with route map, traffic control plan and insurance certificate

☐ Route runs: police or traffic control booked where the city requires it

## Team and money

☐ Chair and leads named: course and safety, money, volunteers, communications, sponsors

☐ Goal set from your own numbers with the profit calculator

☐ Funding model chosen: entry fee, donations, or both

☐ Budget approved with a spending ceiling for the chair

☐ Two-person rule set for counting cash

☐ Sponsor letters and packet sent

## Course and safety

☐ Course measured and mapped, with start, finish, water and first aid marked

☐ Accessible route or loop identified for walkers, wheelchairs and strollers

☐ Medical lead named and first-aid post planned

☐ Heat plan written with the trigger and the person who makes the call

☐ Lightning plan written, with a shelter big enough for everyone

☐ Lost-child plan and a meeting point set

☐ Waiver or permission form reviewed by whoever advises your group

## Registration and pledges

☐ Lap runs: pledge sheets printed with a per-lap cap and return date

☐ Online donation page tested end to end

☐ Route runs: registration form with waiver, fee, shirt size and cutoff date

☐ Kickoff assembly or launch announcement done

☐ Photo opt-out list from the school in hand

☐ Mid-campaign update sent, with no money leaderboard

## Volunteers

☐ Roles and counts set from the course planner, plus backups

☐ Volunteer screening done to your district's or group's rules

☐ Shifts assigned and job cards printed

☐ Adult marshals with vests at every crossing and turn (teens can hand out water, cheer, count laps or help at check-in with an adult lead, but never marshal)

## Final week

☐ Course walked with the course lead and the medical lead

☐ Volunteers confirmed by name; backups on standby

☐ Forecast checked against the heat and lightning plan

☐ Sound system, timer and announcer script tested

☐ Course marked, check-in and finish area set up the day before

## Event day

☐ Volunteer briefing before the first heat or wave

☐ First aid in place before anyone runs

☐ Lap runs: heats run to the clock; lap cards collected per class

☐ Route runs: waves started; sweep behind the last walker; finishers recorded

☐ Cash counted by two people and sealed before it leaves the site

☐ Course cleared and trash removed

## After the event

☐ Totals sent to any per-lap or per-mile donors within two days

☐ Volunteers, sponsors, teachers and staff thanked

☐ Collection closed; deposit made; books reconciled

☐ Receipts and disclosures sent where required

☐ Results note sent to families

☐ Debrief numbers filled in on the Debrief tab of the fun run budget spreadsheet: participants, share who collected, donors, gross, costs, net, net per participant, pledge collection rate, sponsorships, volunteers, unfilled shifts, incidents, timing vs. plan

☐ Family and volunteer survey sent within a week

☐ Debrief held and keep, change and stop notes saved for next year

## Fun run supply list

☐ Course markers: cones, flags or chalk

☐ Start and finish banners or signs

☐ Sound system, microphone and a backup timer

☐ Water, cups and trash bags

☐ First-aid kit, ice packs and the medical lead's contact sheet

☐ Safety vests for every marshal

☐ Clipboards, pens and printed run sheets

☐ Check-in tables, rosters and name tags for volunteers

☐ Lap runs: lap cards or tally sheets, hole punches or markers, class bins

☐ Lap runs: shade for waiting classes

☐ Route runs: bibs and safety pins

☐ Route runs: finish chute materials and a finish-recording sheet

☐ Route runs: barricades and signs required by the permit

☐ Route runs: portable toilets, with accessible units (at least 5 percent and never fewer than one, per the ADA National Network's event guide)

☐ Cash box, deposit bags and a two-signature count sheet