# Jog-a-Thon Planning Checklist

## Approval and team (8 weeks out)

☐ Principal approves date, time window and site

☐ Rain date or heat date chosen

☐ PE teacher agrees to heat schedule and pacing practice

☐ Chair named; leads named for course and counting, volunteers, communications, treasurer, safety

☐ One-page event charter filled in and initialed

☐ District or PTA rules checked for outdoor events, insurance and handling money

☐ Shared folder created for the roster, budget and lap spreadsheet

## Goal, budget and pledges (7 weeks out)

☐ Net goal set and tied to a specific purchase or program

☐ Expense list drafted (shirts, printing, cones, water, prizes, fees)

☐ Goal worked backward with the per-lap pledge planner

☐ Pledge model chosen: capped per-lap, flat, or both

☐ Per-lap cap amount written into the charter

☐ Payment methods decided (cash, check, online) and who handles each

☐ Due date for pledges set (about two weeks after the event)

## Course and schedule (6 weeks out)

☐ Site chosen and loop measured (see course setup)

☐ Lane rule set: walkers inside, passing on the outside

☐ Checkpoint location and number of counting lanes decided

☐ Counting method chosen (see lap counting)

☐ Counters needed per heat calculated, plus one backup

☐ Heat schedule drafted by grade (see the event-day schedule and wave planner)

☐ Indoor or rainy-day backup plan written

## Safety (5 weeks out)

☐ Safety plan reviewed with the school nurse (see the safety plan)

☐ Weather and heat decision makers named

☐ Water and shade locations marked on the course map

☐ First-aid post staffed; AED location confirmed

☐ Process for families to share medical needs through the nurse

☐ Lost-child and release procedure set

☐ Accessible route and participation options confirmed for students who use mobility devices or can't run

## Communications and kickoff (4 to 3 weeks out)

☐ Family letter written (see letter templates)

☐ Pledge sheets and lap cards printed from the printable pledge sheet

☐ Online donation page set up and tested, if used

☐ Kickoff assembly scheduled (see the kickoff guide)

☐ Packets sent home the day of kickoff

☐ Prize tiers announced (see prize ideas)

☐ Weekly progress update scheduled for each Friday until the event

## Volunteers (4 to 1 weeks out)

☐ Roles and counts set (see the volunteer guide)

☐ Volunteer request sent with specific shifts

☐ Background check or visitor rules checked with the school office

☐ Counters, marshals, water, first aid and data-entry shifts filled

☐ Job cards printed for each post

☐ Ten-minute counter training scheduled before the first heat

## Rehearsal and final week

☐ Pacing practice held in PE: start easy, walk when needed, keep moving

☐ Counting rehearsal with crossings timed

☐ Volunteer roster confirmed by message

☐ Heat outlook and forecast checked

☐ Family reminder sent: shoes, water bottle, sunscreen, light clothing

☐ Labeled envelopes ready for lap cards by class

☐ Sound system and playlist tested

## Event day

☐ Course coned and flagged; lanes marked

☐ Water, shade and first aid in place

☐ Volunteers briefed and at posts

☐ Each heat started on time with a 10-minute gap between heats

☐ Lap cards collected by class after each heat, never sent home

☐ Laps entered into the spreadsheet before the data team leaves

☐ Course cleared and equipment returned

## After the event (1 to 3 weeks)

☐ Donor statements sent within 48 hours with the cap applied (see collecting pledges)

☐ Reminder at one week; final reminder at two weeks

☐ Cash and checks counted by two people and the count sheet signed

☐ Online payments reconciled against the pledge list

☐ Deposit made to the school or PTA account

☐ Receipts sent where required (see receipts and taxes)

☐ Results note sent to families and staff

☐ Volunteers thanked by name

☐ Debrief held and notes saved for next year

## Jog-a-thon supply list

☐ Cones for the full loop plus extras for counting lanes

☐ Flags or stakes for turns and the start line

☐ Measuring wheel or a borrowed track measurement

☐ Lap cards (one per runner plus 10% spares) and hole punches or markers for counters

☐ Clipboards, pens and class rosters for each counting lane

☐ Labeled envelopes or bins for lap cards by class

☐ Water coolers, cups, and a trash and recycling station

☐ Pop-up canopies or shaded areas for rest and first aid

☐ First-aid kit, ice packs, and the nurse's supplies

☐ Sound system, extension cords and the playlist

☐ Volunteer vests or lanyards so counters are easy to find

☐ Signs: start/finish, counting lanes by class, water, first aid

☐ Laptop or tablet with the lap spreadsheet, plus a paper backup

☐ Sunscreen and a lost-and-found bin